## Sheet1
ASC OP TF5
Action Items | 2011-08-15
Action | Due Date | Status | Responsible Person | Comments
Finalize Kickoff Notes | 2011-08-16 | Complete | R. Youngworth
Circulate Freeform Proposal Information | 2011-09-15 | Open | D. Aikens | Follow-on will be volunteer(s) for international participation
Goals and Charter Documented | 2011-09-30 | Open | R. Youngworth | Starts as a 'living document'
Send R. Youngworth contact info for M. Bray | 2011-09-08 | Open | D. Aikens
R. Youngworth contact M. Bray for French delegation outreach | 2011-09-22 | Open | R. Youngworth
Document what is in current standards | 2011-09-30 | Open | R. Youngworth | Track what needs further input and editing
Document current formalisms and circulate | 2011-09-30 | Open | R. Youngworth | Further input will be requested
Check with Jessica Nelson on Optimax OSA Incubator meeting participation | 2011-10-07 | Open | R. Youngworth | Follow up would be to see relevance of discussions for TF5
Check on QED participation in OSA Incubator meeting participation | 2011-10-07 | Complete | C. Supranowitz | Greg Forbes will be present; Follow up is to see relevance of discussions for TF5
Compose and track list of known relevant meetings and activities | 2011-09-30 | Open | R. Youngworth | Living document, will always look for input from people present for our activity
Key: Blue are activities where volunteer is welcome
Next Teleconference
11:00 EST on 12 Jan 12