## TF5 Data Overview & Charter
This spreadsheet contains information being tracked for OEOSC ASC OP/TF5 on aspheres. It contains five sheets total with the following topics:
1 - Introduction and Goals/TF5 Charter
2 - Current Tally of Action Items for TF5
3 - A listing of where aspheres appear or are particularly relevant in ANSI/ISO standards
4 - Current formalisms for describing aspheric surfaces
5 - Known meetings and activities that may involve technical details and facets for standards
6 - Tabled ideas
Contact Author: Rich Youngworth; +1-303-747-6065; ryoungworth@riyo-llc.com
Date of last revision: 23 February 2012
Charter and Goals for OEOSC ASC OP/TF5
TF5 is concerned with coordinating standards community efforts in the the rapidly evolving area of aspheric surfaces, most notably any issues that relate to standardization. This includes emerging technologies for the representation, design, measurement, and fabrication of such surfaces. The group will vote based on any standards as directed by the OEOSC, for international or ANSI purposes.
Efforts the group in which the group will engage may vary over time, but likely will include review, voting on, and generation of standards documents; tracking of technology; and dissemination of information to the general community.

## Action Items List
ASC OP TF5
Action Items | 2012-11-30
Action | Due Date | Status | Responsible Person | Comments
Finalize Kickoff Notes | 2011-08-16 | Complete | R. Youngworth
Circulate Freeform Proposal Information | 2011-09-15 | Complete | D. Aikens | Follow-on will be volunteer(s) for international participation
Goals and Charter Documented | 2011-09-30 | Complete | R. Youngworth | Starts as a 'living document'
Send R. Youngworth contact info for M. Bray | 2011-09-08 | Complete | D. Aikens
R. Youngworth contact M. Bray for French delegation outreach | 2011-09-22 | Complete | R. Youngworth | courtesy e-mail sent
Check with Jessica Nelson on Optimax OSA Incubator meeting participation | 2011-10-07 | Complete | R. Youngworth | Follow up would be to see relevance of discussions for TF5
Check on QED participation in OSA Incubator meeting participation | 2011-10-07 | Complete | C. Supranowitz | Greg Forbes will be present; Follow up is to see relevance of discussions for TF5
Give input to S. Kiontke on ISO10110-12 draft and J. Jahn on Freeform WD | 2011-11-30 | Complete | R. Youngworth | effort on -19 next will be team (below)
Obtain Latest Freeform Proposal From Dirk Jahn | 2012-01-31 | Complete | R. Youngworth | Sent by Jahn
Contact Dr. Medicus from Optimax about | 2012-01-31 | Complete | R. Youngworth | Further action below
See if OSA Incubator meeting had minutes | 2012-02-17 | Complete | R. Youngworth | No meeting minutes per Dr. Thompson, he will send us a white paper if one appears
Schedule Next Teleconference | 2012-04-13 | Complete | R. Youngworth | Date is 8 May 2012, limited to one hour
Set up call with K. Medicus, C. Evans, and D. Aikens on Asphere Metrology | 2012-03-05 | Complete | R. Youngworth | Will report to group at next teleconference; will include update to aspheres in metrology standards
TF5 to provide input on -19 WD | 2012-02-27 | Complete | Group | Informal, return info to R. Youngworth
Distribute current versions of ISO10110-5 and ISO10110-6 for reference | 2012-06-21 | Closed | D. Aikens | Preferred if everyone in TF5 signs up for ISO TC172/SC to to see standards and availability
Complete feedback for OP1.0110-12 | 2012-06-30 | Closed | Group | Feedback should be completed and back for submission for vote. R. Youngworth will send edited version to D. Aikens
TF5 to provide input on ISO10110-12 for FDIS | 2012-06-30 | Closed | Group | Send feedback to R. Youngworth
Identify asphere expert to go to ISO10110 international meeting | 2012-07-24 | Closed | R. Youngworth / D. Aikens | Meeting in St. Gallen, Switzerland at end of Oct. or early Nov. 2012
Group Teleconference | 2012-09-18 | Closed | Group | Limited to one hour, update and prep for St. Gallen international meeting
Document what is in current standards, cast votes, give input | Continuing | In-progress | Group | Track what needs further input and editing
Document current formalisms and circulate | Continuing | In-progress | Group | Further input requested from the group
Compose and track list of known relevant meetings and activities | Continuing | In-progress | Group | Living document, will always look for input from people present for our activity
Group Telenconference | 2012-05-08 | Closed | Group | Limited to one hour
Follow up on current asphere metrology standard | 2012-10-03 | Closed | R. Youngworth / K. Medicus
Review two versions of -12 (ISO and ANSI) to provide feedback for international input | 2012-10-15 | Closed | Group | St. Gallen ISO meeting in late October will be important for determining international standards direction
Review C. Evans definition of freeform versus current German ISO10110-19 draft to disambiguate "freeform" | 2012-10-15 | Closed | Group | For St. Gallen meeting, the German perception is that a freeform is “any complex surface”. C. Evans offered that a freeform surface has no axis of rotation.
Review of new Zemax commercial part drawing capabilities | 2012-12-07 | Open | D. Aikens | Emphasis on freeform types of parts
Asphere metrology draft outline | 2012-12-07 | Open | K. Medicus | PINS completed,Medicus et al. generate a document; team develop schedule
Report on St. Gallen meeting | 2012-12-07 | Closed | R. Youngworth | ANSI and ISO versions of standards- will be done at Jan 15, 2013 meeting
Next meeting | 2013-01-15 | Open | Group
Key
Black are done
Red are group
Blue are active
Next Meetings/Teleconferences
Tuesday, 15 January 2013 | 11:00 EDT
Tuesday, 7 May 2013 | 11:00 EDT

## Aspheres in ANSI ISO Standards
Standard Document | Comments on Asphere Inclusion or Importance
ISO10110-5 (Surface Form) | Freeform information to be included per -19
ISO10110-6 (Centration) | Freeform information to be included per -19
ISO10110-8 (Waviness) | Ripple, waviness, etc included in this std
ISO10110-12 (Aspheres) | Aspheric drawing standard
ISO10110-14 (Wavefront) | Zernikes mentioned to
ISO10110-19 (Freeforms) | Aspheric drawing standard - non-symmetric std
14999 Part 5 | Interferometric measurement of surfaces

## Current Asphere Formalisms
OEOSC Formalism Tracking
ASC OP/TF5
Formalism - description | References | Local or Global Basis | Imaging, Illumination, both? | Axial symmetry | Maturity level | Material Comments | Metrology | Benefits/Deficiencies | Risks
Monomial series (z = conic base + a4 r^4 + a6 r^6 + …) | Very common | Global | Both, a lot of imaging | Yes | Very mature, in all shops and volumes | No restrictions | No restrictions | Significant digits and lack of orthogonality | Hard to use but very common in industry
Anamorphic Asphere | Optical Design Code Reference Manual | Global | Imaging | No | Production (e.g. progressive contact lenses) | Suited well for diamond turnable materials | Requires null optics/CGH
X-Y Polynomial | Optical Design Code Reference Manual | Global | Illumination some imaging | No | Production | Moldable materials | Requires null optics/CGH, no metrology for illumination | Lack of orthogonality
Phi-Polynomial (Zernike) (z = base conic + FRINGE Zernike) | Optical Design Code Reference Manual | Global | Imaging | No | Research, some development with diamond turning | Suited well for diamond turnable materials | Requires multiple component nulls | Orthogonal | Confusion between various sets of Zernikes between fabricator and designer
Forbes nonsymmetric polynomial (Zernike-"ish" Q-type) | To be published (OPEX) | Global | Investigated for both imaging and nonimaging | No | Research | No restrictions | Unknown (formalism may help reduce metrology requirements) | Orthogonal, designed with slope constraints in mind.
Allows for quantification of mid-spatials
NURBS | Common | Local | Illumination mostly | No | Development | Moldable materials | Little metrology for illumination | Can describe entire sphere (no sign change)
Difficult to relay to manufacturing (usually converted to other formalism for before fabrication)
Radial Basis Functions | "Meshfree Approximation Method with Matlab" by Gregory E. Fasshauer | Local | Imaging | No | Research, some development with diamond turning |  | Requires null optics/CGH
Others to investigate
Superconics
Wasserman-Wolf
Need to incorporate -12 and -19 formalisms
Wavelet Transforms
Torics
Gram Polynomials
Implicitly Definted Surfaces
Chebyshev
Tabor
Annularly orthogonal polynomials
Others … details/corrections on any too

## Known Meetings and Activities
Known Meetings and Activities | Sponsor | Dates | Location | Comments
ASPE Spring Topical Mtg | ASPE | Spring 2013 | Raleigh, NC, USA | Freeform meeting?
Optics and Photonics | SPIE | 2013-08-01 | San Diego, CA, USA
Optifab | SPIE | 406790 | Barcelona, Spain
Other?

## Tabled Ideas
Idea | Comments
TF5 provide book feedback on aspheric elements book | Braunecker mentioned US input would be welcome, no action taken or currently planned
Disseminate information via technical article | Timing early for TF5, note -19 will be discussed by Kiontke at OF&T (separate from this effort)