## TF5 Data Overview & Charter
This spreadsheet contains information being tracked for OEOSC ASC OP/TF5 on aspheres. It contains five sheets total with the following topics:
1 - Introduction and Goals/TF5 Charter
2 - Current Tally of Action Items for TF5
3 - A listing of where aspheres appear or are particularly relevant in ANSI/ISO standards
4 - Current formalisms for describing aspheric surfaces
5 - Known meetings and activities that may involve technical details and facets for standards
6 - Tabled ideas
Contact Author: Rich Youngworth; +1-303-747-6065; ryoungworth@riyo-llc.com
Date of last revision: 23 February 2012
Charter and Goals for OEOSC ASC OP/TF5
TF5 is concerned with coordinating standards community efforts in the the rapidly evolving area of aspheric surfaces, most notably any issues that relate to standardization. This includes emerging technologies for the representation, design, measurement, and fabrication of such surfaces. The group will vote based on any standards as directed by the OEOSC, for international or ANSI purposes.
Efforts the group in which the group will engage may vary over time, but likely will include review, voting on, and generation of standards documents; tracking of technology; and dissemination of information to the general community.

## Action Items List
ASC OP TF5 Aspheric Optics
Action Items | 2015-03-01
Action | Due Date | Status | Responsible Person | Comments
Rebuild OP1.006 Team and set regular calls | 2015-03-27 | Open | R. Youngworth | Can include new draft leader, otherwise will be Youngworth
Verify scope of OP1.006 | 2015-04-10 | Open | Draft Leader, Group | Group will verify
Set draft schedule for OP1.006 | 2015-05-01 | Open | Draft Leader, Group | Group will verify
Next meeting | 2015-09-08 | Open | Group | Proposed Date (Tuesday) - Time 11-Noon EDT
Key
Black are done
Red are group
Blue are active
Next Meetings/Teleconferences
2015-09-08 | 11:00 EDT | -4 GMT/UTC